## Sheet1
| Task List | Project: River Watch
1 | Understanding existing code |  | Day(s)
| a) Understand how nodes(stations) on map are connected to graph |  | 1 | DONE
| b) Understand the graph library (at introduction level) |  | 1 | DONE
| c) Understand Graph functionality - how it was made, left right panel division etc. |  | 3
| d) Understand XML parsing mechanism |  | 1
| e) Understand existing JS Data Structure to store data and how it's being used |  | 1
2 | Embed ArGIS map instead of Google map
| a) Embed basic ArcGIS map |  | 0 | DONE
| b) Add node to the maps (with proper image, currently it's showing black dots) |  | 1
| c) Link node to graph |  | 1 | DONE
| d) Troubleshoot to make looks identical as original (this task may not require) |  | 2
3 | XML Handling
| a) Implement mechanism to get data from new XML |  | 1
| b) Defince data structure in JS so that it works with the graph |  | 2
| c) Handle missing data (is it always -999?) |  | 0.5
| d) Test on various types of data scenario (specially, missing data) |  | 2
4 | Enhance flood forecast graph
| a) Implement column graph to line graph |  | 1
| b) Implement 5 days actual water level on left side |  | 2
| c) Implement 5 days predicted water level on right side |  | 2
| d) Implement mobile friendly graph (no zoom is required when display size changes) |  | 1
| e) Implement tooltip to graph (date, time, water elevation) |  | 1
| f) Implement expanded graph ( to show more spacing between hourly data points) |  | 3
| g) Implement Handling of missing data (show label for missing data in graph) |  | 1